SQL Server 2019

Large-Table Migration Strategy

Proof of Concept

Module 1b: Migrating Billion-Row Tables to a Partitioned State

Prepared by: Justin Hunter

Prepared for: Walgreens Automated Fulfillment
Date: February 22, 2026

Environment: SQL Server 2019 | Enterprise Edition | SAN-Attached

MODULAR POC SERIES

Module 1b of 6

CONFIDENTIAL

Table of Contents

Executive Summary	1

1. Scope of Migration	1

2. Decision Framework: Which Approach?	1

3. Approach A: In-Place Rebuild	1

3.1 When to Use In-Place Rebuild	1

3.2 Mechanism	1

4. Approach B: Side-by-Side Migration	1

4.1 Step 1: Create the Partitioned Target Table	1

4.2 Step 2: Migration Tracking Table	1

4.3 Step 3: Batch Migration Procedure	1

4.4 Step 4: Delta Synchronization	1

4.5 Step 5: Data Integrity Validation	1

4.6 Step 6: Cutover	1

5. Production Timeline Estimates	1

6. Production Considerations	1

6.1 Transaction Log Management	1

6.2 SAN I/O Management	1

6.3 Nonclustered Index Strategy	1

6.4 Compression During Migration	1

6.5 Current Fragmentation Impact	1

7. Recommended Migration Sequence	1

8. Rollback and Safety	1

9. POC Module Roadmap	1

# Executive Summary

This document is Module 1b of the POC series, focused on the practical challenge of migrating large existing tables from a non-partitioned state to a partitioned state in a live production OLTP environment. While Module 1 covered the theory and component architecture of partitioning, this module addresses the operational reality: how do you partition a table that already contains 1.83 billion rows (OeStatusTrail) or occupies 2.44 TB of storage (OeOrderTextDocument) without unacceptable downtime or risk?

Two migration approaches are evaluated: in-place rebuild (which converts the clustered index onto a partition scheme) and side-by-side migration (which creates a new partitioned table, batch-copies data, and performs a metadata-only name swap). For the PharmAssist environment where the 20 Tier 1 tables collectively hold 2.26 billion rows and 233 GB of data, the side-by-side approach is the only responsible choice for any table exceeding 100 million rows.

The module provides production-ready stored procedures for batch migration with watermark tracking, delta synchronization via ModifiedDate or Change Tracking, and a cutover plan measured in seconds rather than hours. An accompanying SQL script (PartitioningPOC_Module1b_Migration.sql) contains all runnable code.

Module 1b Goal Provide a repeatable, resumable, low-risk migration path for converting the 20 Tier 1 PharmAssist tables to partitioned state with near-zero production downtime, controllable transaction log impact, and full rollback capability at every stage.

# 1. Scope of Migration

The Tier 1 classification from the consolidated analysis (Module 6) identifies 20 tables that are candidates for partition SWITCH-based lifecycle management. These tables share common characteristics: they have a datetime column suitable as a partition key, they follow a hot/cold access pattern with data active for approximately 60 days, and critically, none of them are foreign key parents — meaning partition SWITCH operations are completely unblocked.

The following table summarizes the migration scope based on actual production metadata collected February 2026:

| Table | Row Count | Size (MB) | Partition Key | Priority |
| --- | --- | --- | --- | --- |
| OeStatusTrail | 1,829,100,000 | 116,182 | EventDtTm | Critical |
| OeOrderHistory | 287,600,000 | 28,493 | DtTm | Critical |
| OeOrderSecondaryData | 230,200,000 | 20,074 | OrderDtTm | Critical |
| OeOrderTextDocument | 117,300,000 | 2,503,000 | DocumentDtTm | Critical |
| OeOrder | 113,400,000 | 27,254 | OrderDtTm | Critical |
| OeOrderThirdPartyPlan | 97,600,000 | 9,600 | OrderDtTm | High |
| OeFlaggedRxs | 84,700,000 | 5,800 | FlagDtTm | High |
| OeOrderShipmentAssoc | 75,000,000 | 4,200 | ShipDtTm | High |
| EvtEvent | 1,126,000,000 | 72,000 | EventDtTm | Critical |
| Other Tier 1 (11 tables) | ~350,000,000 | ~18,000 | Various | Medium |

Storage Dominance: OeOrderTextDocument While OeStatusTrail leads by row count (1.83B), OeOrderTextDocument dominates storage at 2.44 TB — 84.6% of the total Tier 1 footprint. This table stores LOB data (document content) and its 1.87 TB index footprint indicates significant optimization opportunity through partition-aligned index restructuring.

# 2. Decision Framework: Which Approach?

There are exactly two viable approaches for converting an existing non-partitioned table to a partitioned table in SQL Server. The choice between them depends primarily on table size, downtime tolerance, and risk appetite.

| Factor | Approach A: In-Place Rebuild | Approach B: Side-by-Side Migration |
| --- | --- | --- |
| Downtime Required | ONLINE rebuild reduces it, but billions of rows still takes HOURS. Final phase acquires Sch-M lock blocking ALL DML. | Near-zero. Original table stays live until the final sp_rename swap (milliseconds). |
| Transaction Log | MASSIVE. Entire rebuild is one implicit transaction. For 1.8B rows expect 2–3x data size in log space (~230–350 GB). | Controllable. Batch inserts with checkpoint between batches. Log stays manageable with 15–30 min backup intervals. |
| Disk Space | 2x table size during rebuild. SAN must absorb this temporarily. | 2x table size (both tables coexist until swap). Same requirement but more predictable. |
| Rollback Safety | DANGEROUS. If rebuild fails hours in, rollback takes equally long. You are stuck. | SAFE. Original table untouched. If migration fails, DROP the new table and retry. |
| Resumability | SQL 2017+ supports RESUMABLE rebuilds, but NOT for partition scheme changes. | Inherently resumable. Track watermark and restart from last completed batch. |
| Complexity | LOW. Single DDL statement. | MEDIUM. Requires batch copy logic, watermark tracking, delta sync, and cutover plan. |
| Verdict | TOO RISKY for tables > 100M rows. | RECOMMENDED for all Tier 1 tables. |

Bottom Line Approach A (in-place rebuild) is acceptable for tables under approximately 100 million rows. For OeStatusTrail (1.83B rows), OeOrderHistory (287M rows), OeOrderSecondaryData (230M rows), OeOrderTextDocument (117M rows / 2.44 TB), OeOrder (113M rows), and EvtEvent (1.13B rows), Approach B is the only responsible choice in a production OLTP system.

# 3. Approach A: In-Place Rebuild

The in-place approach rebuilds the clustered index ON the partition scheme, which physically redistributes all rows into the correct partitions. It is a single DDL statement, which makes it attractively simple. However, at the scale of the PharmAssist Tier 1 tables, the operational risks are severe.

## 3.1 When to Use In-Place Rebuild

| Criterion | Requirement |
| --- | --- |
| Table row count | Under 100 million rows |
| Maintenance window | Several hours available with no production traffic |
| Transaction log capacity | Can handle 2–5x the data size in log space |
| Rollback tolerance | Can absorb a full rollback if the rebuild fails |
| PharmAssist candidates | Potentially the 11 smaller Tier 1 tables (< 100M rows each, ~350M total) |

## 3.2 Mechanism

The process involves three steps: (1) ensure the partition function, scheme, and filegroups exist, (2) drop any non-aligned unique constraints or indexes, and (3) rebuild the clustered index ON the partition scheme. With Enterprise Edition, the rebuild can use ONLINE = ON to reduce blocking, though the final phase still requires a Sch-M lock. For tables under 100M rows, total time is typically under 30 minutes.

The accompanying SQL script demonstrates this approach with a SmallLookupTable example, including verification queries that confirm partition distribution after the rebuild.

# 4. Approach B: Side-by-Side Migration

This is the production-grade approach for the large Tier 1 tables. The strategy creates a new empty partitioned table alongside the existing table, batch-copies data in controlled chunks with watermark tracking, synchronizes any delta changes that occurred during migration, and performs a millisecond metadata-only name swap for cutover.

The original table remains fully operational throughout the entire migration. Transaction log impact is controllable through batch sizing. The process is inherently resumable — if interrupted, it restarts from the last completed watermark. Rollback at any point before cutover is simply DROP TABLE on the new table.

## 4.1 Step 1: Create the Partitioned Target Table

The new table must have identical columns, data types, nullability, and defaults. The only structural difference is that it is created ON the partition scheme. Foreign key constraints are deliberately omitted during migration to avoid FK validation overhead on each batch insert. They are added post-cutover.

IDENTITY Column Handling When copying data from a table with an IDENTITY column, the new table should declare the column without IDENTITY (or use SET IDENTITY_INSERT ON during the copy). The original IDENTITY values are preserved exactly. After cutover, if the column needs IDENTITY behavior for new inserts, either add a SEQUENCE object or re-enable IDENTITY with the correct seed value.

## 4.2 Step 2: Migration Tracking Table

A MigrationLog table tracks every batch: start time, end time, row count, ID range watermarks, duration, rows-per-second throughput, and status (Running, Complete, Failed, DryRun). This provides full auditability of the migration, real-time progress monitoring, and the resume capability that makes the approach resilient to interruptions.

## 4.3 Step 3: Batch Migration Procedure

The usp_MigrateTransactions_Batch procedure (generalized as usp_MigrateTable_Batch for each target table) copies data in controlled chunks. Key design decisions:

| Design Decision | Detail |
| --- | --- |
| Batch Strategy | Copy by primary key ID ranges (not date ranges). Sequential IDs provide predictable batch sizes and simple watermark tracking. |
| Batch Size | Start with 500,000 rows per batch. Too small = excessive commit overhead. Too large = transaction log pressure. Tune based on observed throughput. |
| TABLOCK Hint | INSERT INTO ... WITH (TABLOCK) enables minimal logging in BULK_LOGGED recovery model, dramatically reducing log volume. |
| Throttle Support | @ThrottleSeconds parameter adds a WAITFOR DELAY between batches to reduce SAN I/O pressure during business hours. |
| Dry Run | @DryRun = 1 logs what WOULD happen without executing any data copy. Always dry-run first. |
| Resume | Procedure queries MigrationLog for the last completed watermark and continues from there automatically. |
| Progress Reports | Every 10th batch prints cumulative progress: total rows, percentage complete, current ID range. |

## 4.4 Step 4: Delta Synchronization

During the hours or days the batch migration runs, the source table remains live. New inserts, updates, and deletes continue. Before cutover, these deltas must be captured and applied to the destination table.

Four delta capture strategies are available, in order of preference:

| # | Strategy | Description | When to Use |
| --- | --- | --- | --- |
| A | ModifiedDate Column | Query source for rows WHERE ModifiedDate > migration start. MERGE into destination. Simplest if the column exists and is reliably maintained. | Recommended |
| B | Change Tracking | Enable Change Tracking on source table BEFORE migration. Query CHANGETABLE() for changes since last sync version. Built into SQL Server, low overhead. | If no ModifiedDate |
| C | CDC | Change Data Capture provides full change history. More overhead but captures complete audit trail during migration. | If audit required |
| D | Trigger-Based | Add a trigger logging changes to a staging table. Process staging table during delta sync. Most invasive approach. | Last resort |

The usp_MigrateTransactions_DeltaSync procedure in the accompanying SQL script implements Option A (ModifiedDate). It uses a MERGE statement that handles inserts, updates, and (optionally) deletes in a single pass. Run delta sync repeatedly until the delta shrinks to a manageable size (hundreds or thousands of rows), then proceed to cutover.

## 4.5 Step 5: Data Integrity Validation

Before cutover, three validation checks must pass: (1) row counts must match between source and destination, (2) a checksum comparison on a sampled subset of rows confirms data fidelity, and (3) partition distribution is verified to confirm rows landed in the correct partitions.

Validation is Non-Negotiable Never proceed to cutover without passing all three validation checks. A row count mismatch indicates data loss or duplication. A checksum mismatch indicates data corruption during copy. An unexpected partition distribution indicates a partition function or key mismatch.

## 4.6 Step 6: Cutover

The cutover is the only moment of real production impact. The sequence:

| Step | Action | Detail |
| --- | --- | --- |
| 1 | Drain connections | Stop application traffic or put the database in restricted mode. Ensure no active transactions hold locks on the target tables. |
| 2 | Final delta sync | Run the delta sync procedure one last time to capture any changes since the last sync. |
| 3 | Final validation | Confirm row counts match. The delta should be zero or negligibly small. |
| 4 | sp_rename swap | Within a single transaction: rename the original table to _OLD, rename the partitioned table to the original name, rename the PK constraint. This is metadata-only (milliseconds). |
| 5 | Resume traffic | Application connections resume. All queries now hit the partitioned table. |
| 6 | Post-cutover tasks | Add foreign keys, rename indexes, update statistics with FULLSCAN, verify application behavior. Keep _OLD table for 1–2 weeks as safety net. |

Rollback Plan If anything goes wrong after sp_rename, rollback is equally instant: rename the partitioned table back to _Partitioned and rename _OLD back to the original name. Total rollback time: milliseconds. The _OLD table is your safety net — never drop it until you have confirmed the partitioned table is operating correctly in production for at least one full business cycle.

# 5. Production Timeline Estimates

The following estimates are based on the actual PharmAssist table sizes and a conservative throughput assumption of 200,000 rows/second (achievable on SAN-attached Enterprise Edition with TABLOCK minimal logging). Actual throughput will vary based on row width, index count, SAN load, and concurrent activity.

| Table | Rows | Size | Est. Copy | With Buffer | Notes |
| --- | --- | --- | --- | --- | --- |
| OeStatusTrail | 1,829M | 116 GB | ~2.5 hours | ~3.8 hours | Critical path table |
| EvtEvent | 1,126M | 72 GB | ~1.6 hours | ~2.4 hours | High row count |
| OeOrderHistory | 287M | 28 GB | ~24 min | ~36 min | Moderate |
| OeOrderSecondaryData | 230M | 20 GB | ~19 min | ~29 min | Moderate |
| OeOrderTextDocument | 117M | 2,503 GB | ~10 min* | ~15 min* | LOB-dominated; I/O bound |
| OeOrder | 113M | 27 GB | ~9 min | ~14 min | Moderate |
| OeOrderThirdPartyPlan | 98M | 9.6 GB | ~8 min | ~12 min | Moderate |
| OeFlaggedRxs | 85M | 5.8 GB | ~7 min | ~11 min | In-place candidate |
| OeOrderShipmentAssoc | 75M | 4.2 GB | ~6 min | ~9 min | In-place candidate |
| Remaining 11 tables | ~350M | ~18 GB | ~29 min | ~44 min | In-place candidates |

* OeOrderTextDocument migration time is I/O-bound due to LOB data; row throughput is misleading. Estimate based on ~2.5 GB/min sustained write.

# 6. Production Considerations

## 6.1 Transaction Log Management

The PharmAssist transaction log is currently 148 GB allocated with only 3.6% utilization, FULL recovery model with LOG_BACKUP reuse wait type and 10 GB auto-growth increments. This configuration is adequate for batch migration provided log backups are taken every 15–30 minutes during the migration window. For additional safety, consider temporarily switching to BULK_LOGGED recovery model during the migration to enable minimal logging for the TABLOCK batch inserts. This reduces log volume by 80–90% but requires a full backup before and after the switch.

## 6.2 SAN I/O Management

Use the @ThrottleSeconds parameter to pace migration during business hours. A 2–5 second throttle between 500K-row batches provides enough breathing room for concurrent OLTP operations. Run at full speed (no throttle) during off-hours maintenance windows. Monitor SAN queue depths and latency throughout; the Module 5 I/O monitoring queries can be used in parallel.

## 6.3 Nonclustered Index Strategy

Two approaches exist for handling NCIs during migration. Option 1 creates NCIs on the new table before migration starts — each batch insert maintains the indexes incrementally, which is slower per-batch but leaves the table ready immediately. Option 2 omits NCIs during migration and creates them after — this is faster overall because a single index build is more efficient than incremental maintenance across thousands of batches. For the PharmAssist tables, Option 2 is recommended for any table exceeding 500 million rows.

## 6.4 Compression During Migration

Cold partitions should receive PAGE compression either during or immediately after migration. The compression tier strategy from Module 4 applies: HOT partitions (0–2 months) remain uncompressed for maximum write throughput, WARM partitions (2–4 months) receive ROW compression, and COLD partitions (4+ months) receive PAGE compression. Applying compression as part of the migration saves a separate pass later.

## 6.5 Current Fragmentation Impact

The production metadata reveals severe fragmentation on several Tier 1 tables: OeOrder PK at 76.3% fragmented with all 11 NC indexes between 63–77%, and SrtShipToteShipmentAssoc PK at 89.4%. This fragmentation is a direct consequence of the current iterative block-delete purge pattern. The side-by-side migration inherently resolves this — data is inserted into the new table in partition key order, resulting in zero fragmentation on the destination. This alone represents a significant performance recovery.

# 7. Recommended Migration Sequence

The 20 Tier 1 tables should be migrated in a deliberate sequence that manages risk, validates the approach on smaller tables first, and accounts for dependencies between tables. The recommended sequence:

| Phase | Name | Tables | Rationale | Duration |
| --- | --- | --- | --- | --- |
| 1 | Pilot | 2–3 smaller Tier 1 tables (< 100M rows) | Validate the migration procedure, establish baseline throughput, identify any environment-specific issues. | 1 day |
| 2 | Mid-tier | OeOrder, OeOrderTextDocument, OeOrderThirdPartyPlan, OeFlaggedRxs | Tables with moderate row counts but significant business importance. OeOrderTextDocument is LOB-heavy and tests I/O throughput. | 2–3 days |
| 3 | Large | OeOrderHistory, OeOrderSecondaryData, OeOrderShipmentAssoc | 287M, 230M, and 75M rows respectively. Validates batch migration at scale. | 1–2 days |
| 4 | Critical path | OeStatusTrail (1.83B rows), EvtEvent (1.13B rows) | The two largest tables. Schedule for a weekend window with full SAN bandwidth. These are the longest-running migrations. | 1 weekend |
| 5 | Cleanup | Remaining Tier 1 tables | Complete the migration of all remaining tables. Most are small enough for in-place rebuild. | 1 day |

Total Estimated Migration Timeline Approximately 1.5–2 weeks of elapsed time for all 20 Tier 1 tables, with the critical-path weekend for OeStatusTrail and EvtEvent. During migration, the production database remains fully operational. The only downtime per table is the cutover swap (seconds).

# 8. Rollback and Safety

Every stage of the side-by-side migration is fully reversible:

| Stage | Rollback Procedure |
| --- | --- |
| During batch copy | DROP the new partitioned table. Original table is untouched. Zero impact. |
| During delta sync | Same as above. DROP and retry. |
| After cutover (sp_rename) | Reverse the rename: rename the partitioned table back to _Partitioned and rename _OLD back to original. Milliseconds. |
| After FK restoration | Drop the newly added FKs, reverse the rename, restore original FKs. |
| After _OLD table dropped | No rollback possible. This is the point of no return. Only drop _OLD after thorough validation (1–2 weeks). |

# 9. POC Module Roadmap

| Module | Topic | Status |
| --- | --- | --- |
| 1 | Fundamentals & Candidate Identification | Complete |
| 1b | Large-Table Migration Strategy | Complete (this document) |
| 2 | Indexing Strategy for Hot/Cold OLTP | Complete |
| 3 | Partition SWITCH Operations & Data Lifecycle | Complete |
| 4 | Partition-Aware Maintenance Plans | Complete |
| 5 | Monitoring & Performance Validation | Complete |
| 6 | Consolidated Recommendations & Implementation | Complete |