## Sheet1
Finding/Opportunity |  | Recommendation/Action | Assigned To | Priority | Expected Outcome | Start Date | Target End Date | Actual End Date | Status | Notes
Table partitioning | Overall performance of the purge process drastically reduced because purge activity is converted to partition switch and truncate | See documentation. Action is tabled for now, IA plans to address in near future. | [6 empty] | Not Started | IA mentioned this is under their radar.
lsp_DbPurgeHistoryData: WHILE EXISTS(SELECT * FROM OeOrderHistory...) redundant table probe per iteration | The main loop (line 130) evaluates WHILE EXISTS(SELECT * FROM OeOrderHistory WHERE HistoryDtTm < @cutoff) on every iteration before populating #BlkOfRxsToDel. This is a redundant seek/scan against a massive table (OeOrderHistory) when the previous iteration's DELETE already tells us whether rows remain. Each probe reads the clustered index to check for qualifying rows. wasted I/O when the loop could simply check if the last batch was empty. | Refactor Plan: 1. Replace WHILE EXISTS(...) with a @@ROWCOUNT-based termination pattern. after the INSERT INTO #BlkOfRxsToDel, check IF @@ROWCOUNT = 0 BREAK. |  | P1 | Eliminate one clustered index seek/scan against OeOrderHistory per loop iteration reduce total reads proportional to number of iterations. Straightforward, low-risk change. |  |  |  | Not Started | This is master purge job. Mentioned with Conner before. No plan from IA yet. They may want to more evidence before bring back to their engineering team to discuss.
lsp_DbPurgeHistoryData: #BlkOfRxsToDel temp table dropped and recreated every iteration | Every pass through the OeOrderHistory WHILE loop (lines 138-152) drops #BlkOfRxsToDel, recreates it, and rebuilds a nonclustered index. This forces the optimizer to recompile all ~40 downstream DELETE statements that join to #BlkOfRxsToDel on every single iteration. Plan compilation is CPU-intensive, generates tempdb allocation/deallocation churn, and prevents plan caching. At 100K-row block sizes against millions of history rows, the loop may execute dozens of times per driver call. | Create #BlkOfRxsToDel once before the WHILE loop with the index already in place. Replace the DROP/CREATE/INDEX sequence inside the loop with TRUNCATE TABLE #BlkOfRxsToDel at the top of each iteration. The ~40 downstream DELETE plans get compiled once and reused across all iterations. |  | P1 | Eliminate dozens of plan recompilations per iteration reduce CPU overhead and tempdb contention plans cached and reused across loop iterations |  |  |  | Not Started | Haven't discussed with IA yet
lsp_DbPurgeHistoryData: Cascade temp tables (#ShpIds, #ManIds, #PalIds, #Grps, #Pats, etc.) are unindexed heaps | During each iteration, the proc populates ~8 cascade temp tables (#ShpIds, #ManIds, #PalIds, #Grps, #Pats, #Prescrs, #RxPats, #GrpPats) to drive orphan detection and cascade deletes. These tables are heaps with no clustered index, no PK. Every downstream DELETE that joins to one of these tables performs a heap scan on the temp table side. If a single iteration yields 15K shipment IDs, every DELETE joining #ShpIds scans all 15K rows. Multiplied across ~40 DELETE statements per iteration, the wasted reads add up quickly. | Add a clustered index or PRIMARY KEY to each cascade temp table after population (or define it at CREATE). For example: CREATE TABLE #ShpIds (ShpId INT PRIMARY KEY CLUSTERED). This converts downstream join scans to seeks. Alternatively, use INSERT INTO ... WITH (TABLOCK) followed by CREATE CLUSTERED INDEX for bulk-load efficiency. |  | P1 | Convert heap scans to index seeks across ~40 DELETE joins per iteration; reduce logical reads proportional to cascade table size × number of downstream joins. Second-highest impact fix after #BlkOfRxsToDel recompilation. |  |  |  | Not Started | Haven't discussed with IA yet
lsp_DbPurgeHistoryData: No TRY/CATCH error handling in main proc | The main purge procedure has no TRY/CATCH anywhere. If any of the ~40 DELETE statements fail mid-iteration (deadlock, timeout, constraint violation), execution continues to the next statement with no rollback, no logging, and no notification to the driver proc. This can leave orphaned partial deletes that subsequent runs trip over repeatedly, leading to cascading failures. | Wrap the main loop body in TRY/CATCH with proper error logging to the event table. On CATCH, log the error, clean up temp tables, and RETURN with an error output parameter so the driver proc knows to stop. Consistent with pattern in lsp_DbDeleteOldEvents (v3). |  | P2 | Prevent silent partial-delete failures; enable driver proc to detect and halt on errors; reduce orphaned data scenarios. Reliability improvement, not direct IOP reduction. |  |  |  | Not Started | Haven't discussed with IA yet
lsp_DbDeleteOldSmartShelfErrors: CTE uses SELECT * instead of SELECT Id | SELECT * reads all 10 columns from SmartShelf.EvtErrorLog when only the clustered key (Id, bigint) is needed for the delete. 10x column overhead per block iteration. Compounded by the WHILE > bug, which prevents the loop from ever executing ... meaning old error rows are never purged. | 1. Narrow CTE from "Select Top(@NumOfRowsBlockSize) * ..." to "Select Top(@NumOfRowsBlockSize) Id ...". 2. Fix WHILE condition operator from > to < on @MaxToDelete (loop never executes today) |  | P3 | Reduced logical reads per block; loop actually executes; consistent with v3 pattern in lsp_DbDeleteOldEvents |  |  |  | Not Started | This is more cosmatic change. No significent performance bumps.
lsp_DbDeleteOldSmartShelfEvents: CTE uses SELECT * instead of SELECT Id | SELECT * reads all 13 columns from SmartShelf.EvtEventLog when only the clustered key (Id, bigint) is needed. 13x column overhead per block iteration. Same WHILE > bug...old event rows are never purged. | 1. Narrow CTE from "Select Top(@NumOfRowsBlockSize) * ..." to "Select Top(@NumOfRowsBlockSize) Id ...". 2. Fix WHILE condition operator from > to < on @MaxToDelete (loop never executes today) |  | P3 | Reduced logical reads per block; loop actually executes; consistent with v3 pattern in lsp_DbDeleteOldEvents |  |  |  | Not Started | This is more cosmatic change. No significent performance bumps.
lsp_DbDeleteOldScriptImages: CTE uses SELECT * instead of PK | SELECT * reads all 7 columns from OeScriptImage including 2 image (LOB) columns (Image, ImageBack) ...when only the clustered key is needed. LOB reads dramatically inflate I/O per block; this is potentially the highest-impact single fix of the five. | 1. Narrow CTE from "Select Top(@NumOfRowsBlockSize) * ..." to select <PK column(s)>. |  | P3 | Dramatic reduction in logical reads per block, especially if table contains wide or LOB columns |  |  |  | Not Started | This is more cosmatic change. No significent performance bumps.
lsp_DbPurgeHistoryData: OeOrderAcceptReject CTE uses SELECT * | SELECT * reads all 50 columns from OeOrderAcceptReject when only Id is needed. 50x column overhead per block across every iteration of the purge driver. | 1. Narrow CTE from "Select Top(@NumOfRowsBlockSize) * ..." to "Select Top(@NumOfRowsBlockSize) Id ...". Note: OeOrderHistory loop already selects OrderId, HistoryDtTm (correct). |  | P3 | Reduced logical reads in the AcceptReject purge loop; consistent pattern across both loops in the procedure |  |  |  | Not Started | This is more cosmatic change. No significent performance bumps.
lsp_DbDeleteOldRxData: OeOrderAcceptReject CTE uses SELECT * | SELECT * reads all 50 columns from OeOrderAcceptReject when only Id is needed. Same 50x overhead as lsp_DbPurgeHistoryData. | 1. Narrow CTE from "Select Top(@NumOfRowsBlockSize) * ..." to "Select Top(@NumOfRowsBlockSize) Id ...". |  | P3 | Reduced logical reads in the AcceptReject purge loop; consistent pattern across both loops in the procedure |  |  |  | Not Started | This is more cosmatic change. No significent performance bumps.
lsp_RxfGetListOfManualFillGroups: Parameter sniffing, correlated subqueries, scalar UDF barrier, table variable cardinality | #1 total reads in March Query Store: 105.5B reads across 162K executions (7 appearances in top 50). Avg duration swings 54ms to 7,058ms...classic parameter sniffing volatility. Joins across OeOrder (44 cols), OeGroup (12 cols), OePriority (3 cols), InvNdcLocAssoc (11 cols). Still appears 4x in April snapshot at 4.6B reads. | v49 refactor is ready and has been shared 1. replaced 9 correlated subqueries with NextDeliveryDay CTE 2. inlined scalar UDF fOrdGroupingCritValForDisplay to STRING_AGG 3. converted @ToteGroups to #ToteGroups 4. assigned local variables for parameter sniffing 5. added missing NOLOCK hint. Ready for testing. |  | P1 | Eliminate plan instability (54ms-7058ms range); reduce per-exec reads from 2.4M to target <100K; remove scalar UDF parallelism barrier; improve cardinality estimates via temp table |  |  |  | In Progress | IA is reviewing the change suggestion. They haven't made change to the code yet.
lsp_SrtGetShipToteIfExists: Double-query barcode lookup, SELECT *, correlated subquery, missing NOLOCK | 27.4M executions in March (6.9B total reads); 20.6M executions in April (6.2B total reads). Called on every tote scan from Package Sorter Status display. Joins SrtShipToteShipmentAssoc (5 cols), OeOrderShipmentAssoc (5 cols), OeOrder (44 cols). High frequency amplifies even small per-exec inefficiencies. | 1. collapsed double-query barcode lookup to single SELECT + NULL check 2. replaced UNION with OR EXISTS 3. narrowed Select * to Select 1 4. removed dead 3-table join 5. replaced correlated subquery with Count(*) Over() 6. added missing NOLOCK. Currently in testing with IA. |  | P1 | Reduce per-exec logical reads; eliminate dead code paths; consistent NOLOCK coverage; measurable reduction in total reads given 20M+ daily executions |  |  |  | Completed | 4/20: Deployed to all MFC sites last week
lsp_ImgGetListOfTopXImagesToMove: LEFT JOIN + OR across two join paths forces suboptimal plan; TOP subquery prevents rowgoal | 8.6B total reads (Mar), 6.4B (Apr) across 5K-8K execs. Avg 2377ms and 1.19M reads per exec. Joins ImgImage (includes image LOB), ImgRxImgAssoc, ImgCanImgAssoc, CanCanister, OeOrderHistory (via view). LEFT JOIN + OR prevents optimizer from choosing efficient seek paths for either branch independently. | v7 refactor near completion/still in progress 1. replaced LEFT JOIN + OR with UNION of two INNER JOIN branches (Shipped Rx path/Verified Canister path) 2. extracted TOP into local @MaxImages variable for rowgoal optimization 3. retained FORCESEEK hints pending post-deployment validation. |  | P2 | Optimizer can apply rowgoal and seek independently per branch; eliminate unnecessary LOB column reads from non-qualifying path; target reduction from 1.19M to <200K reads per exec |  |  |  | In Progress | Haven't discussed with IA yet. Justin is still testing.
lsp_ShpGetOrdersForTopReadyToShipGroup: Triple-repeated correlated FOR XML PATH subquery; repeated correlated subqueries for multi-vial split check | 10.0B total reads (Mar), 10.3B (Apr) across 259K-274K execs. Appears 4x in both Query Store snapshots under 2 qry ids. Block 4 repeats identical STUFF/FOR XML PATH logic 3 times across the UNION...each execution runs the same correlated join to OeOrder (44 cols), OeOrderPoNumAssoc (4 cols), OeOrderShipmentAssoc (5 cols) three times. Blocks 2 and 3 each contain a correlated scalar subquery for the multi-vial split check against OeOrder. | Refactor Plan: consolidate the 3 temp tables into a single UNION ALL (they already have distinct GroupType labels), run the FOR XML PATH correlated subquery once against the combined set Extract the multi-vial split check into a temp table or CTE computed once for remaining parts. Replace legacy Object_Id temp table checks with DROP TABLE IF EXISTS. |  | P3 | Reduce the FOR XML PATH correlated subquery from 3 executions per call to 1; eliminate repeated correlated scalar subqueries; target 30-50% reduction in per-exec reads from current 60K-80K avg |  |  |  | In Progress | Haven't discussed with IA yet
lsp_SrtGetSortationItems: Catch-all query anti-pattern (OR @Param IS NULL) forces table scan on 4-column table | 5.1B total reads (Mar), 3.2B (Apr) across 34K-58K execs. Avg 264ms and 95K reads per exec for a simple lookup against SrtSortationItem. The WHERE (@Barcode IS NULL OR Barcode = @Barcode) pattern prevents the optimizer from using an index seek; it generates a scan plan that must evaluate every row. Production = local = v2, no refactor written. | Refactor Plan: 1. Replace catch-all OR pattern with OPTION(RECOMPILE) to allow the optimizer to short-circuit NULL parameters at runtime OR 2. Use dynamic SQL with parameterized sp_executesql for each parameter combination. |  | P2 | Convert table scans to index seeks when parameters are provided (majority case); target reduction from 95K to <100 reads per exec for single-row lookups by Barcode |  |  |  | In Progress | Haven't discussed with IA yet. Justin is still testing.
lsp_SrtGetNumOfStoresWithAndWithoutSorterLocs (v6): 4 UNION branches with duplicated SrtSorterLoc→SysEndPharmacy join chain; NOT IN subqueries with NULL risk; TRIM on every row | 4.2B total reads (April, 17.3K execs, 242K avg reads/exec), 3.0B total reads (March, 17.2K execs, 173K avg reads/exec). Four UNION branches each independently join SrtSorterLoc (13 cols) → SysEndPharmacyShpCarrierAssoc (4 cols) → SysEndPharmacy (26 cols)...the identical 3-table join chain is repeated 4 times. Priority 1 and 4 both use NOT IN subqueries which are NULL-unsafe (if any StoreNum in the subquery is NULL, the entire NOT IN returns no rows). TRIM(O.StoreNum) = TRIM(@StoreNum) is applied on every row, preventing index seeks on StoreNum. | Consolidate 4 UNION branches into a single pass: compute store-to-sorter-loc assignment once in a CTE or temp table, then derive Priority via CASE WHEN (unassigned+active orders=1, assigned+no tote=2, assigned+full=3, unassigned+no orders=4). Replace NOT IN with NOT EXISTS to avoid NULL-safety issues. Replace TRIM comparisons with a pre-trimmed local variable: SET @StoreNum = TRIM(@StoreNum), then compare directly. Production = local = v6, no refactor written. |  | P1 | Reduce the 3-table join from 4 executions to 1 per call; eliminate NOT IN NULL risk; enable index seeks on StoreNum. Target reduction from 242K to <60K reads per exec. |  |  |  | Not Started
lsp_OrdGetRxStatusCounts: WHILE loop CSV parsing; 100% duplicated SELECT block (38 CASE WHEN aggregations × 2); table variable @RestrictAddrBank without statistics | 557M total reads (April, 1.3K execs, 419K avg reads/exec), 1.1B total reads (March, 2K execs, 556K avg reads/exec). The proc has two completely duplicated SELECT blocks (one for @CountOnlyMostRecentRxForEachOrderId=1, one for =0). Each block has 38 SUM(CASE WHEN...) aggregations across a 4-way UNION ALL of OeOrder (44 cols), OeOrderHistory (with indexhint), OeOrderCurrHistoryDtTm, and OeRxRequest. The WHILE loop parses a CSV @AddrBankFilter into @RestrictAddrBank (table variable, no statistics). The EXISTS subquery against @RestrictAddrBank uses ambiguous column reference (Where AddrBank = AddrBank compares to itself always true). | Replace WHILE CSV parser with STRING_SPLIT or a single INSERT...SELECT from a splitter. Eliminate code duplication: the only difference between the two branches is whether OeOrderHistory joins OeOrderCurrHistoryDtTm...use a single SELECT with a conditional JOIN or CTE. Convert @RestrictAddrBank to #RestrictAddrBank (temp table) for cardinality estimates. Fix the EXISTS subquery: 'Where AddrBank = AddrBank' should reference the outer table alias (e.g., 'Where rb.AddrBank = O.AddrBank'). Production = local, no version number, no refactor written. |  | P3 | Eliminate WHILE loop overhead; halve the query surface by removing duplicate block; fix incorrect EXISTS filter (currently a no-op — always true); improve cardinality on bank filter. Moderate exec volume but high per-exec cost. |  |  |  | Not Started
lsp_RxvGetRxsQueuedForVerification (v7): 5 temp tables in cascade; duplicate INSERT into #QueuedRxs (ImgImage vs ImgImage_IntId); config reads on every call; complex nested OR/AND filter | 787M total reads (March, 199K execs, 4.0K avg reads/exec). Proc creates 5 temp tables (#QueuedRxs, #LocationNdcs, #AuditRxs, #RxList, #SemiAutoFillBanks). The #QueuedRxs table is populated by two nearly identical INSERT statements...one LEFT JOINing ImgImage, the other INNER JOINing ImgImage_IntId...that could be a single UNION ALL. Two separate config lookups against vCfgSystemParamVal on every execution (values unlikely to change within a session). The main WHERE clause has a 4-level nested OR/AND condition for the canister verification logic that prevents clean index usage. | Merge the two INSERT INTO #QueuedRxs blocks into a single INSERT...SELECT with UNION ALL across ImgImage and ImgImage_IntId. Cache config values as session-level or pass as parameters from the caller. Simplify the nested OR/AND: pre-compute @ExcludeAutoFill = CASE WHEN @CfgRxInheritsCanisterVerification = 1 THEN 1 ELSE 0 END and use it as a flat filter. Consider merging #AuditRxs and #RxList into a single temp table. Add indexes on #RxList(OrderId, HistoryDtTm) before the ImgRxImgAssoc join. Production = local = v7, no refactor written. |  | P3 | Reduce temp table count from 5 to 3; eliminate duplicate image-table INSERT; improve join performance with indexed temp tables. Target reduction from 4K to <1.5K reads per exec at 199K execs/month. |  |  |  | Not Started
lsp_PmssIwebGetTopQueuedTrx (v2): High-frequency queue poller (6.8M–9M execs/month); simple structure but massive cumulative reads | 3.1B total reads (March, 6.8M execs, 458 avg reads/exec) plus 871M reads (March second snapshot, 2.3M execs, 386 avg reads/exec). Ccombined ~9M execs/month. Simple SELECT TOP 1 from PmssCapturedXmlTrxs (9 cols) WHERE TrxStateCode = 'Q' ORDER BY Id. The proc is written well, but at 9M+ execs/month, even 400 reads/exec accumulates to 3-4B total. | Verify index coverage: if no index exists on (TrxStateCode, Id), create one — this should reduce reads from ~400 to <10 per exec. If TrxStream is a large column (XML/varchar(max)), a filtered index on TrxStateCode = 'Q' with INCLUDE (TrxKey, Trx, TrxStream) would be optimal. Also evaluate caller polling frequency — 9M execs/month suggests a tight polling loop that may benefit from a WAITFOR DELAY or Service Broker queue pattern. Production = local = v2, no refactor written. |  | P3 | With proper index: reduce per-exec reads from ~400 to <10, saving ~3.5B reads/month. Proc code change is minimal (possibly none — the win is an index addition). Polling frequency reduction could further cut exec count. |  |  |  | Not Started
lsp_RbtDetermineNextVialToProcess (v10): 4 separate COUNT(*) queries against same tables; SELECT * from #temp_table2; heap temp table; redundant subquery in EXISTS check | 1.4B total reads (March, 189K execs, 7.4K avg reads/exec). Four independent COUNT(*) queries at the top of the proc scan overlapping tables (OeOrder, TcdStatus, RbtQueuedForResetTcds) with similar WHERE filters — these could be consolidated into fewer passes. Priority 3 branch creates #temp_table2 as a heap, populates it via EXEC lsp_OrdGetReadyForDispenseRxsInBank, then does SELECT * FROM #temp_table2 WITH (NOLOCK) ORDER BY ActOnAsPriInternal — the ORDER BY on an unindexed heap requires a sort. The EXISTS check for large vial availability uses a nested TOP 1 subquery inside an EXISTS. | Consolidate the 4 COUNT queries: use a single SELECT with conditional aggregation (SUM(CASE WHEN ... THEN 1 ELSE 0 END)) across a UNION ALL of the base tables, or at minimum combine the OeOrder and TcdStatus counts that share the @AddrBank filter. Replace SELECT * with explicit column list on #temp_table2. Add a clustered index on #temp_table2(ActOnAsPriInternal, PriInternal) before the final SELECT to eliminate the sort. Simplify the vial supply EXISTS to a straightforward TOP 1 check. Production = local = v10, no refactor written. |  | P3 | Reduce 4 table scans to 1-2 via consolidated aggregation; eliminate sort on temp table; cleaner code. Target reduction from 7.4K to <3K reads per exec across 189K execs/month. |  |  |  | Not Started